{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":124,"n_cols":6,"rows_kept":124,"merged":[[0,0,0,5],[2,1,8,1],[9,1,14,1],[15,1,23,1],[24,1,61,1],[62,1,68,1],[69,1,76,1],[77,1,86,1],[87,1,88,1],[89,1,98,1],[100,1,101,1],[102,1,103,1],[104,1,107,1],[108,1,110,1],[111,1,116,1],[117,1,123,1]],"flags":["formulas_cached_only"]}
["台风救灾维修项目清单"]
[null,"类别","立项号","项目","进度","估算（元）"]
[1,"外围墙",587,"湖光校区东区二饭堂路边围墙和运动场围墙台风刮到修复工程","完成",15000]
[2,null,663,"东区月岭小学及水厂外围墙","施工中",310000]
[3,null,6876,"海滨校区女生大院外围墙及运动场10米围墙","完成",186709]
[4,null,null,"海滨校区运动场西边大门","完成"]
[5,null,662,"霞山校区西十栋东南角处修复台风受损围墙","完成",20000]
[6,null,661,"霞山校区东一栋修复台风受损地面消防通道大门","完成",40000]
[7,null,null,"海滨校区运动场围墙（20米）、宿舍挡土墙及护栏","预算中",50000]
[8,"水电",584,"东海岛电路、路灯的抢修","完成",80000]
[9,null,589,"采购路灯抢修材料 ","完成",94100]
[10,null,788,"湖光校区电房和泵房维修","施工中",40000]
[11,null,null,"海滨校区路灯","完成"]
[12,null,547,"霞山校区路灯设施维修","完成",13700]
[13,null,"零星","中心电房门窗","完成",5800]
[14,"食堂",605,"湖光校区学生第三食堂维修台风受损设施","完成",20000]
[15,null,619,"湖光校区学生第二食堂维修台风受损设施","基本完成",60000]
[16,null,567,"维修学生第二食堂受台风损坏抽排系统","完成",36000]
[17,null,634,"海滨校区学生第六食堂维修台风受损部分设施","完成",25000]
[18,null,643,"湖光校区学生第一食堂维修台风受损部分设施","完成",40000]
[19,null,638,"第四食堂维修台风受损部分设施","完成",30000]
[20,null,609,"教工饭堂维修","完成",86000]
[21,null,673,"第五食堂（霞山校区）维修","完成",35000]
[22,null,777,"湖光校区第四食堂门厅天棚","预算中",350000]
[23,"学生宿舍",608,"湖光校区海虹学生公寓维修台风受损设施","完成",15000]
[24,null,623,"湖光校区海涵学生公寓大门维修台风受损设施","完成",15000]
[25,null,607,"湖光校区海乐学生公寓维修受损院子大门","完成",30000]
[26,null,625,"湖光校区海燕学生公寓宿舍维修台风受损设施","完成",15000]
[27,null,611,"湖光校区海月学生宿舍院子维修台风部分受损围墙及洗衣房","完成",10000]
[28,null,615,"湖光校区海轩A、B维修台风受损宿舍部分门窗","完成",20000]
[29,null,617,"湖光校区海宁A、B维修台风受损宿舍部分门窗","完成",118632]
[30,null,618,"湖光校区海沁维修台风受损部分围墙","完成",40000]
[31,null,599,"湖光校区海天A、B栋学生公寓维修台风受损设施","完成",75000]
[32,null,602,"湖光校区海云学生公寓围墙维修台风受损设施","完成",9594]
[33,null,603,"湖光校区海安A、B栋学生公寓维修台风受损设施","完成",65000]
[34,null,604,"湖光校区海趣学生宿舍院子维修台风部分受损围墙","完成",15000]
[35,null,595,"湖光校区海虹A、B栋学生公寓修复台风受损设施","完成",20000]
[36,null,624,"湖光校区海情A、B栋学生公寓维修台风受损设施","完成",15000]
[37,null,627,"湖光校区海韵A、B栋学生公寓大门维修台风受损设施","完成",80000]
[38,null,"零星","海滨校区1号宿舍楼围墙","完成",5000]
[39,null,630,"湖光校区海花A、B维修台风受损宿舍部分门窗","完成",10000]
[40,null,632,"湖光校区海涛A、B维修台风受损宿舍部分门窗","完成",85000]
[41,null,633,"湖光校区海怀学生大院维修部分台风受损围墙","完成",85000]
[42,null,635,"湖光校区海乐A、B维修台风受损宿舍部分门窗","完成",30000]
[43,null,636,"湖光校区海宇A、B维修台风受损宿舍部分门窗","完成",76000]
[44,null,7085,"海滨校区学生宿舍台风受损抢修 ","完成",77000]
[45,null,640,"湖光校区海霞A、B维修台风受损宿舍部分门窗","完成",90000]
[46,null,644,"湖光校区海燕学生公寓围墙维修台风受损设施","完成",10000]
[47,null,641,"湖光校区海浪A、B栋学生公寓维修台风受损设施","完成",15000]
[48,null,645,"霞山校区一号楼学生宿舍维修台风受损宿舍部分窗户玻璃","完成",10000]
[49,null,649,"湖光校区海鹰学生公寓维修台风受损宿舍部分门窗","完成",67000]
[50,null,647,"湖光校区海景A、B学生公寓宿舍维修台风受损门窗设施","完成",95000]
[51,null,648,"湖光校区海涵学生公寓宿舍维修台风受损门窗设施","完成",31000]
[52,null,646,"湖光校区海鹰学生公寓维修台风受损部分围墙","完成",16000]
[53,null,650,"湖光校区海云A、B维修台风受损宿舍部分门窗","完成",26000]
[54,null,651,"湖光校区海欢学生公寓院子大门维修台风受损","完成",10000]
[55,null,653,"湖光校区海沁A、B、C栋学生公寓维修台风受损设施","完成",25000]
[56,null,796,"湖光校区海月A、B栋学生公寓维修台风受损设施 ","完成",80000]
[57,null,820,"湖光校区西区学生公寓台风损坏设施补充维修","施工中",50000]
[58,null,819,"湖光校区东中区学生公寓台风损坏设施补充维修","施工中",57000]
[59,null,639,"湖光校区海风A、B维修台风受损宿舍部分门窗","完成",20000]
[60,null,"？","学生公寓仓库维修","未报"]
[61,"教室",616,"湖光校区主教学楼维修台风受损部分设施","完成",180000]
[62,null,601,"湖光校区兴教楼外语学院维修台风受损设施","完成",20000]
[63,null,591,"海滨校区台风后抢修海滨校区教学实验等公共楼房门窗 ","完成",53000]
[64,null,"666\\836","第二教学楼、钟海楼维修","施工中",114000]
[65,null,"零星","霞山校区A、B楼窗维修","完成",9500]
[66,null,585,"艺术学院剧场顶补漏(划转经费）","基建处负责",50000]
[67,null,628,"湖光校区中歌艺术学院维修台风受损部分设施","完成",83440]
[68,"实验室",612,"湖光校区科技楼修复台风受损部分设施","施工中",125000]
[69,null,613,"湖光校区农学院动物医院维修台风受损部分设施","施工中",30000]
[70,null,606,"湖光校区水生生物博物馆维修台风受损设施","完成",111000]
[71,null,626,"湖光校区兴海楼食品科技维修台风受损设施","施工中",50000]
[72,null,629,"湖光校区农学院兴农楼维修台风受损部分设施（含屋顶设施）","施工中",125000]
[73,null,642,"湖光校区第三实验楼维修台风受损设施","基本完成",80000]
[74,null,"？","湖光校区第三实验楼楼顶风罩","待定制",50000]
[75,null,"会议纪要","水产科技楼西南角3-5层及大门维修","完成",200000]
[76,"实验基地",687,"东海岛基地车间及实验室","开工",380000]
[77,null,680,"东海岛腐蚀试验场围栏和照明灯设施","完成",25000]
[78,null,803,"农学院后山动科基地（牛舍墙体及鸡舍屋顶、围墙等）","待审批",370000]
[79,null,717,"农学院林果基地","施工中",50000]
[80,null,714,"牧草基地","开工",50000]
[81,null,7908,"农学院动物医院拆除东面外墙装饰铁条","施工中",25000]
[82,null,778,"航海学院霞山校区台风受损房屋维修","完成",13000]
[83,null,"？","农学院水稻灌溉渠道（链接简易水塔至田间）","方案待定"]
[84,null,784,"生物中心楼顶温室","基建处实施",800000]
[85,null,"？","南三岛基地建筑物及设施维修","工程量未确定"]
[86,"图书馆",614,"湖光校区图书馆维修台风受损设施","基本完成",46000]
[87,null,null,"图书馆顶琉璃瓦","基建处立项",60000]
[88,"体育场馆",527,"体育馆维修门窗","施工中",90000]
[89,null,null,"体育馆顶棚","基建处立项",100000]
[90,null,856,"湖光校区网球场围网及灯光","待审批",430000]
[91,null,652,"湖光校区棒垒球场修复台风受损设施","完成",15000]
[92,null,655,"湖光校区游泳池维修台风受损设施","完成",10000]
[93,null,656,"湖光校区东区田径运动区设施台风受损设施","完成",25000]
[94,null,7863,"湖光校区东区田径运动场跑道维修台风受损设施","完成",80000]
[95,null,null,"霞山网球场损坏的灯柱","建议清理"]
[96,null,7821,"海滨校区体育场围网修复","完成",65000]
[97,null,671,"沙滩排球场围墙","完成",160000]
[98,"校医院",622,"湖光校区校医院维修台风受损设施","完成",90000]
[99,"招待所",600,"湖光校区18栋教师午休房维修台风受损设施 ","完成",10000]
[100,null,7488,"湖光校区18栋教师午休房围墙","完成",13000]
[101,"社团场所",660,"湖光校区礼堂门维修台风受损大门","完成",10000]
[102,null,"零星","学生活动中心墙体","完成",10000]
[103,"周转房",654,"艺术学院湖光校区24栋教职工公用住房修复台风受损设施","施工",22000]
[104,null,"零星","教工周转房（分批次或校区实施）","完成",90000]
[105,null,657,"海洋与气象学院湖光校区部分教职工公用住房修复台风受损设施 ","基本完成",18000]
[106,null,658,"湖光校区保卫处职工公用住房修复台风受损部分设施","施工中",28000]
[107,"办公室",610,"霞山校区东一幢401思政部办公室修复台风受损","完成",20000]
[108,null,"校友捐赠","湖光校区行政楼顶维修（基建处）","完工",300000]
[109,null,795,"继续教育学院办公室","完成",30000]
[110,"招牌及标识","校友捐赠","学校大门招牌","完工",136000]
[111,null,620,"海滨校区大门口警务室及园岭路维修台风受损部分设施","完成",20000]
[112,null,"零星","绿林路二区值班室、卷砸门","完成",9500]
[113,null,659,"湖光校区修复台风受损部分交通标志路牌","完成",95000]
[114,null,"零星","霞山校区修复台风受损部分交通标志路牌","完成",7000]
[115,null,"零星","霞山保卫科门牌","完成",8000]
[116,"其他","?","湖光校区车库","工程量未确定"]
[117,null,670,"道路塌方（游泳场附近）","完成",40000]
[118,null,669,"湖光校区候车厅维修","完成",35000]
[119,null,703,"树木倒伏后周边人行道砖修复","完成",70000]
[120,null,null,"防台风沙袋","完成",5975]
[121,null,808,"楼宇字牌设计、加固、测试等费用","部分完成",70000]
[122,null,null,"综合服务中心台风期间雇佣民工清理湖光校区人工费","完成",88900]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}